## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 | 2023-11-12
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Look for code smells in source code. | Day 0: 3; Day 1: 1; Day 2: 2
2 | Identify GoF patterns. | Day 0: 6; Day 2: 2; Day 3: 4
3 | Analyze metric data. | Day 0: 2; Day 1: 2
4 | Create Use Case Diagrams. | Day 0: 4; Day 2: 3; Day 3: 1
5 | Review peers. | Day 0: 2; Day 2: 1; Day 3: 1
6 | Fix work according to reviews. | Day 0: 3; Day 3: 3
Completed Effort |  | 0 | 3 | 8 | 9 | 0 | 0 | 0 | 0
Remaining Effort |  | 20 | 17 | 9 | 0 | 0 | 0 | 0 | 0
Ideal Burndown |  | 20 | 17.1429 | 14.2857 | 11.4286 | 8.5714 | 5.7143 | 2.8571 | 0