## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Look for code smells in source code | Day 0: 4; Day 6: 1; Day 7: 3
2 | Identify gof patterns | Day 0: 4; Day 7: 4
3 | Analyze metrics | Day 0: 3; Day 2: 2; Day 7: 1
4 | Setup metrics in IntelliJ | bar: Day 0 to Day 1
5 | Use Case Diagrams | Day 0: 4; Day 6: 3; Day 7: 1
6 | Assing code segments to team members | Day 0: 4; Day 6: 2; Day 7: 2
Completed Effort |  | 0 | 1 | 2 | 0 | 0 | 0 | 6 | 11 | Note: There were tests in this week
Remaining Effort |  | 20 | 19 | 17 | 17 | 17 | 17 | 11 | 0
Ideal Burndown |  | 20 | 17.1429 | 14.2857 | 11.4286 | 8.5714 | 5.7143 | 2.8571 | 0