## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-21 | 2021-12-22
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Create User Stories for functionalities. | bar: Day 0
2 | Create AuthorInformationTab extending FieldsEditorTab. | bar: Day 0
3 | Create Fields for AuthorInformationTab and display them in it. | Day 0: 2
4 | Find proper data extraction API (Wikidata-Toolkit chosen). | bar: Day 0
5 | Create dynamic group and subgroup creation functionality. | Day 0: 2
6 | Study and examine Wikidata API code. | bar: Day 0
7 | Make parser for Author Name and for Time Value. | bar: Day 0
8 | Make parser for Link to get title from Wikidata. | bar: Day 0
9 | Create WikidataFetcher data extraction logic. | Day 0: 4
10 | Update standard fields to display. | bar: Day 0
11 | Implement EntryBasedParserFetcher interface functions in WikidataFetcher. | Day 0: 2
12 | Create tests for WikidataFetcher (first functionality). | bar: Day 0
13 | Create tests for GroupTreeViewModel (second functionality). | bar: Day 0
14 | Record functionalities demonstration video. | bar: Day 0
Completed Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining Effort |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Ideal Burndown |  | 20 | 17.1429 | 14.2857 | 11.4286 | 8.5714 | 5.7143 | 2.8571 | 0