## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-24 | 2021-12-25 | 2021-12-26 | 2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
1 | Create User Stories for functionalities. | 1 | 2021-12-16: 0.5; 2021-12-17: 0.5
2 | Create AuthorInformationTab extending FieldsEditorTab. | 1 | bar: 2021-12-22
3 | Create Fields for AuthorInformationTab and display them in it. | 2 | 2021-12-22: 2
4 | Find proper data extraction API (Wikidata-Toolkit chosen). | 1 | bar: 2021-12-22
5 | Create dynamic group and subgroup creation functionality. | 2 | 2021-12-26: 2
6 | Study and examine Wikidata API code. | 1 | bar: 2021-12-27
7 | Make parser for Author Name and for Time Value. | 1 | bar: 2021-12-27
8 | Make parser for Link to get title from Wikidata. | 1 | bar: 2021-12-27
9 | Create WikidataFetcher data extraction logic. | 4 | 2021-12-28: 3; 2021-12-29: 1
10 | Update standard fields to display. | 1 | bar: 2021-12-28
11 | Implement EntryBasedParserFetcher interface functions in WikidataFetcher. | 2 | 2021-12-29: 2
12 | Create tests for WikidataFetcher (first functionality). | 1 | bar: 2021-12-29
13 | Create tests for GroupTreeViewModel (second functionality). | 1 | bar: 2021-12-29
14 | Record functionalities demonstration video. | 1 | 2021-12-29: 0.5; 2021-12-30: 0.5
Completed Effort |  | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 2 | 3 | 4 | 5.5 | 0.5
Remaining Effort |  | 20 | 19.5 | 19 | 19 | 19 | 19 | 19 | 15 | 15 | 15 | 15 | 13 | 10 | 6 | 0.5 | 0
Ideal Burndown |  | 20 | 18.6667 | 17.3333 | 16 | 14.6667 | 13.3333 | 12 | 10.6667 | 9.3333 | 8 | 6.6667 | 5.3333 | 4 | 2.6667 | 1.3333 | 0