## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24 | 2023-11-25 | 2023-11-26
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Implementing gunpowder and ammunition.
1.1 | Adding gunpowder good and resource, alongside the necessary messages and a placeholder image | Day 0: 0.5; Day 1: 0.5
1.2 | Added ammunition good type | Day 0: 0.5; Day 1: 0.5
1.3 | Added ammunition logic | 3 |  |  | 1 | 1 |  | 0.5 | 0.5
1.4 | Added ammunition production building | bar: Day 0; Day 6
1.5 | Added roles for spending ammuntion | Day 0: 2; Day 4: 1; Day 5: 0.5; Day 6: 0.5
2 | Implementing caves exploration and mining.
2.1 | Added cave tile item | bar: Day 0 to Day 1
2.2 | Added cave logic | Day 0: 2; Day 2: 1; Day 6: 1
2.3 | Unit interation with cave | Day 0: 3; Day 1: 1; Day 5: 1; Day 6: 1
2.4 | Added cave item image and XML references | bar: Day 0; Day 4
3 | Implementing the combat feature, allowing the claim of the enemy boat.
3.1 | Added function to capture ship | bar: Day 0; Day 2
3.2 | Added a button to enable capturing ship | bar: Day 0; Day 6
3.3 | Debugging | 4 | 1 |  | 1 | 1 |  | 1
Completed Effort |  | 0 | 4 | 2 | 2 | 4 | 1.5 | 6 | 0.5
Remaining Effort |  | 20 | 16 | 14 | 12 | 8 | 6.5 | 0.5 | 0
Ideal Burndown |  | 20 | 17.1429 | 14.2857 | 11.4286 | 8.5714 | 5.7143 | 2.8571 | 0