## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Gunpowder and ammunition clean-up and Unit tests.
1.1 | Merge branches and resolved conflicts with Mines-of-Moria. | Day 0: 0.5; Day 3: 0.5
1.2 | Added Cave tile. | Day 0: 2; Day 2: 2
1.3 | Made Cave tile items spawn exclusively on Cave tiles. | bar: Day 0; Day 2
1.4 | Added Unit tests. | Day 0: 2; Day 2: 2
1.5 | Bug fixes. | Day 0: 1.5; Day 1: 0.5; Day 3: 0.5; Day 4: 0.5
2 | Caves clean-up and Unit tests.
2.1 | Added Unit tests. | Day 0: 2; Day 2: 2
2.2 | Bug fixes. | Day 0: 2; Day 2: 1; Day 3: 1
3 | Enemy boat claiming clean-up and Unit tests.
3.1 | Implemented message after combat. | Day 0: 2; Day 3: 2
3.2 | Implemented success probability. | Day 0: 2; Day 3: 2
3.3 | Bug fixes. | bar: Day 0; Day 3
3.4 | Added Unit tests. | bar: Day 0; Day 3
4 | Merge remaining branches and resolve conflicts | Day 0: 2; Day 4: 2
5 | Recorded demonstration video. | Day 0: 2; Day 4: 0.5; Day 5: 1.5
6 | Created final report | bar: Day 0; Day 5
Completed Effort |  | 0 | 0 | 8 | 7 | 0 | 0 | 0 | 0
Remaining Effort |  | 20 | 20 | 12 | 5 | 5 | 5 | 5 | 5
Ideal Burndown |  | 20 | 17.1429 | 14.2857 | 11.4286 | 8.5714 | 5.7143 | 2.8571 | 0