## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-22
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Set up the gitHub repository | Day 0: 4; Day 4: 2; Day 5: 2
2 | Set up the game | Day 0: 3; Day 5: 3
3 | Test the game | Day 0: 5; Day 5: 3; Day 6: 2
4 | Prepare the structure of future scrums, burndown charts and sprints | Day 0: 3; Day 5: 2
5 | First quick look at the code | Day 0: 5; Day 6: 2
Completed Effort |  | 0 | 0 | 0 | 0 | 2 | 10 | 4 | 0
Remaining Effort |  | 20 | 20 | 20 | 20 | 18 | 8 | 4 | 4
Ideal Burndown |  | 20 | 17.1429 | 14.2857 | 11.4286 | 8.5714 | 5.7143 | 2.8571 | 0