## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Set up the gitHub repository | Day 0: 4; Day 1: 4
2 | Set up the game | Day 0: 3; Day 1: 3
3 | Test the game | Day 0: 4; Day 1: 2; Day 2: 1; Day 5: 1
4 | Prepare the structure of future scrums, burndown charts and sprints | Day 0: 3; Day 2: 2; Day 5: 1
5 | First quick look at the code | Day 0: 4; Day 1: 2; Day 2: 1; Day 5: 1
6 | Define User Stories | Day 0: 2; Day 5: 2
Completed Effort |  | 0 | 11 | 4 | 0 | 0 | 5 | 0 | 0
Remaining Effort |  | 20 | 9 | 5 | 5 | 5 | 0 | 0 | 0
Ideal Burndown |  | 20 | 17.1429 | 14.2857 | 11.4286 | 8.5714 | 5.7143 | 2.8571 | 0