## Week 1
Week 1
Task ID | Task Description
1 | Set up the gitHub repository
2 | Set up the game
3 | Test the game
4 | Prepare the structure of future scrums, burndown charts and sprints
5 | First quick look at the code
6 | Define User Stories

## Week 2
Week 2
Task ID | Task Description
1 | Look for code smells in source code
2 | Identify gof patterns
3 | Analyze metrics
4 | Setup metrics in IntelliJ
5 | Use Case Diagrams
6 | Assign code segments to team members

## Week 3
Week 3
Task ID | Task Description
1 | Look for code smells in source code.
2 | Identify GoF patterns.
3 | Analyze metric data.
4 | Create Use Case Diagrams.
5 | Review peers.
6 | Fix work according to reviews.

## Week 4
Week 4
Task ID | Task Description
1 | Adding gunpowder good and resource, alongside the necessary messages and a placeholder image.
2 | Implementing caves exploration.
3 | Implementing the combat feature allowing to gain the enemy boat.

## Week 5
Week 5 tasks
Task ID | Task Description
1 | Implementing gunpowder and ammunition.
1.1 | Adding gunpowder good and resource, alongside the necessary messages and a placeholder image
1.2 | Added ammunition good type
1.3 | Added ammunition logic
1.4 | Added ammunition production building
1.5 | Added roles for spending ammuntion
2 | Implementing caves exploration and mining.
2.1 | Added cave tile item
2.2 | Added cave logic
2.3 | Unit interation with cave
2.4 | Added cave item image and XML references
3 | Implementing the combat feature, allowing the claim of the enemy boat.
3.1 | Added function to capture ship
3.2 | Added a button to enable capturing ship
3.3 | Debugging

## Week 6
Week 6
Task ID | Task Description
1 | Gunpowder and ammunition clean-up and Unit tests.
1.1 | Merge branches and resolved conflicts with Mines-of-Moria.
1.2 | Added Cave tile.
1.3 | Made Cave tile items spawn exclusively on Cave tiles.
1.4 | Added Unit tests.
1.5 | Bug fixes.
2 | Caves clean-up and Unit tests.
2.1 | Added Unit tests.
2.2 | Bug fixes.
3 | Enemy boat claiming clean-up and Unit tests.
3.1 | Implemented message after combat.
3.2 | Implemented success probability.
3.3 | Bug fixes.
3.4 | Added Unit tests.
4 | Merge remaining branches and resolve conflicts.
5 | Recorded demonstration video.
6 | Created final report.