## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Adding gunpowder good and resource, alongside the necessary messages and a placeholder image. | Day 0: 7; Day 6: 1; Day 7: 1
2 | Implementing caves exploration. | Day 0: 6; Day 6: 1; Day 7: 1
3 | Implementing the combat feature allowing to gain the enemy boat. | Day 0: 7; Day 5: 1; Day 7: 1
Completed Effort |  | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3
Remaining Effort |  | 20 | 20 | 20 | 20 | 20 | 19 | 17 | 14
Ideal Burndown |  | 20 | 17.1429 | 14.2857 | 11.4286 | 8.5714 | 5.7143 | 2.8571 | 0